## 2019 (hidden)
No. | Activities | [5 empty] | Q4 | [12 empty] | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4
|  |  | Per | Timing | Responsible | Receiver(s) | Jan |  |  |  |  | Feb |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | Sept |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | March
|  |  |  | CET |  |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W49 | W49 | W50 | W51 | W52 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
101 | • | Annual General Meeting - Annual Report - Proposdal for Director's Report - Budget Proposal - Elect chairman of the board - Adoption of precedural rules for Board of Directors - Adoption of work instructions for MD - Decision to teckna bolagets firma | Year | 1-4 -- 30/9 | MD | Board
102 | • | Ordinary Board Meeting - Brief Management report: summary of financial & strategic development - Rolling 3-month liquidity report, if there are concerns - Balans och resultat report - Forecast for CFY against budget | Quarter | Jun, Sep, Dec, Mar | MD | Board | August W35: 28; Dec W51: 18; March W13: 25
103 | •
100 | Board / Styrelse
201 | • | End of year party | Year |  |  |  | Dec W51: 18
202 | • | Performance Appraisals | Year | bar: May W18 to May W22
203 | • | Performance feedback | Quarter | bar: June W23 to June W26
204 | • | Consultancy profile (start, end assignment, sales cycle) | Year | bar: June W23 to June W26; Dec W49 to Dec W52
205 | • | bar: June W23 to June W26
206 | • | bar: June W23 to June W26
207 | •
200 | Human Resources
300 | • | Book-keeping: reconcile bank transactions | Day/week |  | Accounts
301 | • | Book-keeping: review G/L accounts, close month. | Month | 1/x? | Accounts | Accountant
302 | • | Vendor invoicing: create, invoice/receipt, VAT, bank payment | Day |  | Accounts
303 | • | Sales invoicing: time reporting, ledger, deliver, VAT | Month | 1/x | Accounts | Customer A/R | bar: Jan W1; Feb W6; March W10; April W14; May W18; June W23; July W27; August W32; Sept W36; Oct W40; Nov W45; Dec W49; Jan W1; Feb W6; March W10
304 | • | Corporate tax: ledger to/from SV, bank payment | Month | 12/x | Accounts | Skatteverket | Dec W50: 12; Jan W3: 17; Feb W7: 12; March W11: 12
305 | • | Payroll tax: declaration, ledger to/from SV, bank payment | Month | +12 | Accounts | Skatteverket | Jan W2: 12; Feb W7: 12
306 | • | VAT declaration previous quarter, ledger, bank payment | Quarter | Q+12 | Accounts | Skatteverket | bar: May W18; August W33; Nov W46; Jan W2
307 | • | VAT deduction | Quarter | Q+1+12 | Accounts | Skatteverket | Feb W7: 12
308 | • | Payroll: payslips, bank payment | Month | 20/x | HR, Accounts | Staff, Skatteverket | Jan W4: 20; Feb W8: 20; March W12: 20; April W16: 20; May W21: 20; June W25: 20; July W29: 20; August W34: 20; Sept W38: 20; Oct W42: 20; Nov W47: 20; Dec W51: 20; Jan W4: 20; Feb W8: 20; March W12: 20
309 | • | Vendor information: FORA, … | Annum | Jan | Accounts | Vendor | bar: Jan W1 to Jan W5; Jan W1 to Jan W3
310 | • | Statement of earnings & deductions | Annum | Jan | Accounts | Staff | bar: Jan W1 to Jan W5
311 | • | Statement of earnings & deductions KU10 + SKV2304 | Annum | Jan | Accounts | Skatteverket | bar: Jan W1 to Jan W5
312 | • | Close year and annual report | Annum | FYE | Accounts | Board, Skatteverket, BV? | bar: April W14 to July W28
313 | • | Dun unpaid invoices | Month | +1w | Accounts | Customer A/R | bar: Dec W49; Jan W1; Feb W6; March W10
314 | • | Pay contractors when invoice payment received | Month | +5d | Accounts | Vendor A/P | bar: Dec W49; Jan W1; Feb W7; March W11
315 | • | Produce reports: balance sheet, income statement (P/L), A/R, A/P. | Quarter | w1 | Accounts | Accountant, Board | bar: May W18 to May W22; August W32 to August W35; Dec W50 to Dec W51; March W10; March W12
316 | • | Tax return | Annum |  | Accounts | bar: Sept W36 to Nov W49
317 | • | Update payment accuracy file (AR Dunning) | Month | w2 | Accounts | CFO, CEO | bar: Jan W2; Feb W7; March W11; April W15; May W19; June W24; July W28; August W33; Sept W37; Oct W41; Nov W46; Dec W50; Jan W2; Feb W7; March W11
300 | Financial
401 | • | Sales Account Planning
402 | • | Business Targets
403 | • | Business Plan
404 | • | ESL Sales Review
400 | Sales
501 | • | Time reporting closed, verified. Save reports to Comptrolling. | Week |  |  |  | Jan W5: 31; Feb W9: 28; March W13: 31; April W17: 30; May W22: 31; June W26: 30; July W31: 31; August W35: 31; Sept W39: 30; Oct W44: 31; Nov W49: 30; Dec W52: 31; Jan W5: 31; Feb W9: 28
502 | bar: Jan W5; Feb W9; March W13; April W17; May W22; June W26; July W31; August W35
503 | bar: Jan W5; Feb W9; March W13; April W17; May W22; June W26; July W31; August W35
504 | bar: Jan W5; Feb W9; March W13; April W17; May W22; June W26; July W31; August W35
500 | Operations

## FY2020 (hidden)
No. | Activities | [5 empty] | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4
|  |  | Per | Timing | Responsible | Receiver(s) | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  |  | March
[7 empty] | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
CET | time axis 2020-03-30 to 2021-03-22
101 | • | Call to Ordinary Annual General Meeting (4-6 weeks prior) - agenda | Annum | 4-6w prior | Board | Shareholders | bar: 2020-03-30 to 2020-05-25; 2021-03-01 to 2021-03-15
102 | • | Annual General Meeting (ordinary) | Annum | < 6 m EOFY | Chairperson | Shareholders | 2020-04-13: 13/4
103 | • | AGM Minutes of Meeting | Annum | within 2 w | Chairperson | Shareholders, on request | bar: 2020-04-20; 2020-05-18 to 2020-06-01
104 | • | Call to Board Meeting | Quarter | 7d prior | Chairperson, MD | Board of Directors, MD | bar: 2020-05-18 to 2020-05-25; 2020-08-17 to 2020-08-24; 2020-11-16 to 2020-11-23
105 | • | Review and update charter for Board of Directors | Annum |  | Board | Board of Directors | bar: 2020-03-30 to 2020-05-25; 2021-03-01
106 | • | Review and update charter for Managing Director | Annum |  | Board | Board of Directors | bar: 2020-03-30 to 2020-05-25; 2021-03-01
107 | • | Generate and analyse metrics for annual report | Annum |  | MD | Board of Directors | bar: 2020-03-30 to 2020-05-11
108 | • | Budget proposal | Annum |  | MD | Board of Directors | bar: 2020-03-30 to 2020-05-11; 2021-03-08 to 2021-03-22
109 | • | Business Plan | Annum |  | MD | Board of Directors | bar: 2020-03-30 to 2020-04-27; 2021-03-08 to 2021-03-22
110 | • | Board Meeting | Quarter | Ju, Se, De, Ma | Chairperson | Board of Directors, MD | 2020-04-20: 22/4; 2020-09-14: 17; 2020-12-14: 16
111 | • | Board Meeting Minutes of Meeting | Quarter | > 7d prior |  | Board of Directors, MD | bar: 2020-03-30 to 2020-04-06; 2020-04-27; 2020-06-22 to 2020-07-06; 2020-09-28 to 2020-10-12; 2020-12-21 to 2021-01-04
100 | Shareholders / Board of Directors
201 | • | End of year party | Annum | bar: 2020-12-14
202 | • | Performance Appraisal | Biannual | bar: 2020-06-22 to 2020-06-29; 2020-11-16
203 | • | Consultancy profile (start, end assignment, sales cycle) | Annum | bar: 2020-11-23 to 2020-12-21
204 | • | Create staff register for new CY | Annum | bar: 2020-12-28
205 | • | Create archive folders for Recruitment | Annum | bar: 2020-12-28
200 | Human Resources
300 | • | Book-keeping: reconcile bank transactions | Day/week |  | Accounts
301 | • | Book-keeping: review G/L accounts, close month. | Month | 1/x? | Accounts | Accountant | 2020-09-07: 8; 2020-12-07: 8; 2021-01-11: 12; 2021-02-08: 8; 2021-03-08: 8
302 | • | End of month report: actual V budget | Month | 15/x | Accounts | MD | 2020-09-07: 8; 2020-12-07: 8; 2021-01-11: 12; 2021-02-08: 8; 2021-03-08: 8
303 | • | Vendor invoicing: create, invoice/receipt, VAT, bank payment | Day |  | Accounts
304 | • | Sales invoicing: invoice, VAT, enter PastDue | Month | 31/x | Accounts | Customer A/R | 2020-03-30: 1; 2020-05-04: 1; 2020-06-01: 1; 2020-06-29: 1; 2020-08-03: 1; 2020-08-31: 1; 2020-09-21: 21; 2020-09-28: 1; 2020-10-26: B3; 2020-11-02: 1; 2020-11-23: B3; 2020-11-30: 1; 2020-12-21: B3; 2020-12-28: 1; 2021-01-04: 4; 2021-01-25: B3; 2021-02-01: 1; 2021-02-22: B3; 2021-03-01: 1
305 | • | Payroll: payslips, bank payment, tax report, tax declaration | Month | 20/x | HR, Accounts | Staff, Skatteverket | 2020-04-20: 20; 2020-05-18: 20; 2020-06-15: 20; 2020-07-20: 20; 2020-08-17: 20; 2020-09-14: 20; 2020-10-12: 20; 2020-11-16: 20; 2020-12-14: 20; 2021-01-18: 20; 2021-02-15: 20; 2021-03-15: 20
306 | • | VAT declaration | Quarter | Q+1+12 | Accounts | Skatteverket | 2020-08-17: 17; 2021-01-11: 12; 2021-02-08: 8
307 | • | Tax bank payment to Skatteverket (payrollx2, corp, VAT) | Month |  | Accounts | Skatteverket | 2021-01-11: 12; 2021-02-08: 8; 2021-03-08: 8
308 | • | Tax withdrawals. Ledger to/from SV (corp, payroll, VAT) | Month | +12 | Accounts | Skatteverket | 2020-04-13: 14; 2020-05-11: 12; 2020-06-08: 12; 2020-07-13: 13; 2020-08-17: 17; 2020-08-24: 25; 2020-09-14: 18; 2020-10-12: 12; 2020-11-09: 12; 2020-12-14: 14; 2021-01-18: 18; 2021-02-08: 12; 2021-03-08: 12
309 | • | Payroll: salaries paid, ledger | Month | 25/x | Accounts | Staff | 2020-04-27: 25; 2020-05-25: 25; 2020-06-22: 25; 2020-07-20: 25; 2020-08-24: 25; 2020-09-21: 25; 2020-10-19: 23; 2020-11-23: 25; 2020-12-21: 23; 2021-01-25: 25; 2021-02-22: 25; 2021-03-22: 25
310 | • | Vendor information: FORA, … | Annum | Jan | Accounts | Vendor | bar: 2021-01-04 to 2021-01-11
311 | • | Statement of earnings & deductions (no more) | Annum | Jan | Accounts | Staff | 2021-01-11: 12
312 | • | Statement of earnings & deductions KU10 + SKV2304, if dividend | Annum | Jan | Accounts | Skatteverket | 2021-01-11: 12
313 | • | Close year and annual report | Annum | FYE | Accounts | Board, Skatteverket, BV? | 2020-11-02: 2
- Request engagemengsrapport from bank | bar: 2020-03-30; 2020-05-04; 2020-06-01; 2020-06-29; 2020-08-03; 2020-08-31; 2020-09-28; 2020-11-02; 2020-11-30; 2021-01-04; 2021-02-01
- Skattekonto utdrag, MOMS & AGI sammanställning FY | bar: 2020-03-30; 2020-05-04; 2020-06-01; 2020-06-29; 2020-08-03; 2020-08-31; 2020-09-28; 2020-11-02; 2020-11-30; 2021-01-04; 2021-02-01
- Beslut debiterad prelskatt FY | bar: 2020-03-30; 2020-05-04; 2020-06-01; 2020-06-29; 2020-08-03; 2020-08-31; 2020-09-28; 2020-11-02; 2020-11-30; 2021-01-04; 2021-02-01
- Accrual for sales and vendor purchase orders | bar: 2020-03-30; 2020-05-04; 2020-06-01; 2020-06-29; 2020-08-03; 2020-08-31; 2020-09-28; 2020-11-02; 2020-11-30; 2021-01-04; 2021-02-01
- Förvaltningsberättelse | bar: 2020-03-30; 2020-05-04; 2020-06-01; 2020-06-29; 2020-08-03; 2020-08-31; 2020-09-28; 2020-11-02; 2020-11-30; 2021-01-04; 2021-02-01
- Annual report sign and submit to BV | bar: 2020-03-30; 2020-05-04; 2020-06-01; 2020-06-29; 2020-08-03; 2020-08-31; 2020-09-28; 2020-11-02; 2020-11-30; 2021-01-04; 2021-02-01
314 | • | Dun unpaid invoices | Month | +1w | Accounts | Customer A/R | bar: 2020-03-30; 2020-05-04; 2020-06-01; 2020-06-29; 2020-08-03; 2020-08-31; 2020-09-28; 2020-11-02; 2020-11-30; 2021-01-04; 2021-02-01; 2021-03-01
315 | • | Pay contractors when invoice payment received, update PastDue | Month | +5d | Accounts | Vendor A/P | 2021-01-04: 5; 2021-02-01: 3
316 | • | Produce reports: balance sheet, income statement (P/L), A/R, A/P. | Quarter | w1 | Accounts | Accountant, Board | 2020-09-07: 8; 2020-12-07: 8
317 | • | Apply prel. tax based on budgeted result | Annum | bar: 2020-05-11 to 2020-05-18
318 | • | Archive verifications for previous year and start new binder. | Annum | bar: 2020-03-30
319 | • | Create archive folder for previous FY: AR, AP, Bank, Comptrol, Time reporting, vendor PO, Taxation, Payroll, Budget | Annum | bar: 2020-03-30
320 | • | Update KYC at bank | Annum |  | Accounts | Bank | bar: 2021-01-04; 2021-03-22
300 | Financial
401 | • | Sales Account Planning
402 | • | Business Targets
403 | • | ESL Sales Review
110 | • | Move opportunities into sales funnel for new FY | Annum | bar: 2020-03-30
400 | Sales
501 | • | Time reports: transfer to Invoicing, Report to Suppliers/Customers | Week |  |  | Antigo, S2HC, NFA | 2020-03-30: 31; 2020-04-27: 30; 2020-05-25: 31; 2020-06-29: 30; 2020-07-20: 25; 2020-07-27: 31; 2020-08-17: 22; 2020-08-31: 31; 2020-09-14: 18; 2020-09-28: 30; 2020-10-19: 24; 2020-10-26: 31; 2020-11-16: B3; 2020-11-30: 30; 2020-12-28: 31; 2021-01-18: B3; 2021-01-25: 31; 2021-02-22: 26
502 | • | Create resource map for next CY | Annum | bar: 2020-12-21 to 2020-12-28
503 | • | Create annual plan for new FY | Annum | bar: 2020-03-30; 2021-03-01 to 2021-03-22
504 | • | Create new action logs for CY and move open actions | Annum | bar: 2020-12-21 to 2020-12-28
505 | • | Create document register for new CY | Annum | bar: 2020-12-21 to 2020-12-28
506 | • | Review and update office handbook | Annum | bar: 2020-12-21 to 2020-12-28
507 | • | Generate, proofread and cut all planR calendars | Annum | bar: 2020-11-30 to 2020-12-21
508 | • | Customer survey | Biannual | Jun, Dec | COO | Customers | 2020-12-07: Dun
509 | • | Staff survey | Biannual | Jun, Dec | COO | Contractors | bar: 2020-11-30 to 2020-12-07
510
511
500 | Operations
Formulas:
Q1 = "W"&WEEKNUM([Q1, row below])

## FY2021 (hidden)
No. | Activities | [5 empty] | Q1 | [13 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4
|  |  | Per | Timing | Responsible | Receiver(s) | April |  |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March
[7 empty] | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
CET | time axis 2021-03-29 to 2022-03-28
101 | • | Call to Ordinary Annual General Meeting (4-6 weeks prior) - agenda | Annum | 4-6w prior | Board | Shareholders | bar: 2021-08-30; 2022-03-14
102 | • | Annual General Meeting (ordinary) | Annum | < 6 m EOFY | Chairperson | Shareholders | 2021-09-27: 30
103 | • | AGM Minutes of Meeting | Annum | within 2 w | Chairperson | Shareholders, on request | 2021-09-27: 30
104 | • | Call to Board Meeting | Quarter | 7d prior | Chairperson, MD | Board of Directors, MD | bar: 2021-03-29 to 2021-04-05; 2021-05-31 to 2021-06-07; 2021-10-18; 2021-11-29; 2022-02-28
105 | • | Review and update charter for Board of Directors (1) | Annum |  | Board | Board of Directors | bar: 2021-04-05 to 2021-04-12; 2021-06-14; 2021-09-27
106 | • | Review and update charter for Managing Director (1) | Annum |  | Board | Board of Directors | bar: 2021-04-05 to 2021-04-12; 2021-06-14; 2021-09-27
107 | • | Generate and analyse metrics for annual report | Annum |  | MD | Board of Directors | bar: 2021-03-29 to 2021-04-19; 2021-05-17; 2021-05-31 to 2021-06-14; 2021-09-27
108 | • | Budget proposal (1) | Annum |  | MD | Board of Directors | bar: 2021-03-29 to 2021-04-19; 2021-05-03 to 2021-06-14; 2021-09-27; 2022-02-28 to 2022-03-07
109 | • | Business Plan | Annum |  | MD | Board of Directors | bar: 2021-03-29 to 2021-04-12; 2021-09-27; 2022-02-28 to 2022-03-07
110 | • | Board Meeting | Quarter | Ju, Se, De, Ma | Chairperson | Board of Directors, MD | 2021-04-12: 13; 2021-06-14: 15; 2021-10-25: 27; 2021-12-13: 15; 2022-03-14: 16
111 | • | Board Meeting Minutes of Meeting | Quarter | > 7d prior |  | Board of Directors, MD | 2021-10-25: 27; 2021-12-13: 16
100 | Shareholders / Board of Directors
201 | • | End of year party | Annum
202 | • | Performance Appraisal | Biannual | bar: 2021-06-21
203 | • | Consultancy profile (start, end assignment, sales cycle) | Annum | bar: 2021-11-29
204 | • | Create staff register for new CY | Annum | bar: 2021-12-27
205 | • | Create archive folders for Recruitment | Annum
200 | Human Resources
300 | • | Book-keeping: reconcile bank transactions | Day/week |  | Accounts |  | 2022-01-10: 10
301 | • | Book-keeping: review G/L accounts, close month. | Month | 1/x? | Accounts | Accountant | 2021-04-05: 8; 2021-05-03: 6; 2021-05-31: Book; 2021-06-07: 7; 2021-07-05: 8; 2021-08-09: 10; 2021-09-06: 7; 2021-10-04: 5; 2021-11-08: 9; 2021-12-06: 7; 2022-01-10: 10; 2022-02-07: 8; 2022-03-07: 8
302 | • | European VAT Summary | Quarter |  |  |  | 2021-03-29: 1; 2021-07-05: 1; 2021-10-04: 5; 2022-01-03: 1; 2022-01-10: 1
303 | • | End of month report: actual V budget | Month | 15/x | Accounts | MD | 2021-04-05: 8; 2021-08-09: 10; 2021-09-06: 7; 2021-10-04: 5; 2021-11-08: 9; 2021-12-06: 7; 2022-01-10: 10; 2022-02-07: 8; 2022-03-07: 8
304 | • | Vendor invoicing: create, invoice/receipt, VAT, bank payment | Day |  | Accounts
305 | • | Sales invoicing: time reporting, ledger, deliver, VAT, enter PastDue | Month | 31/x | Accounts | Customer A/R | 2021-03-29: 31; 2021-04-26: 30; 2021-05-31: 31; 2021-06-28: 30; 2021-07-26: 30; 2021-08-23: B3; 2021-08-30: 31; 2021-09-20: B3; 2021-09-27: 30,3; 2021-10-25: 29,31; 2021-11-22: 28; 2021-11-29: 30; 2021-12-20: 23; 2021-12-27: 31; 2022-01-24: 28; 2022-01-31: 31; 2022-02-21: 26; 2022-02-28: 28; 2022-03-21: 26; 2022-03-28: 31
306 | • | Payroll: payslips, bank payment, tax report, tax declaration | Month | 20/x | HR, Accounts | Staff, Skatteverket | 2021-04-19: 20; 2021-05-17: 20; 2021-06-14: 18; 2021-06-21: 20; 2021-07-19: 20; 2021-08-16: 20; 2021-09-20: 20; 2021-10-18: 20; 2021-11-15: 20; 2021-12-20: 20; 2022-01-17: 20; 2022-02-14: 20; 2022-03-14: 18
307 | • | VAT declaration | Quarter | Q+1+12 | Accounts | Skatteverket | 2021-05-03: 6; 2021-08-09: 10; 2021-11-08: 9; 2022-02-07: 8
308 | • | Tax bank payment to Skatteverket (payrollx2, corp, VAT) | Month |  | Accounts | Skatteverket | 2021-04-05: 8; 2021-08-09: 10; 2021-10-04: 5; 2021-11-08: 9; 2021-12-06: 7; 2022-01-10: 10; 2022-02-07: 8; 2022-03-07: 8
309 | • | Tax withdrawals. Ledger to/from SV (corp, payroll, VAT) | Month | +12 | Accounts | Skatteverket | 2021-04-12: 14; 2021-05-10: 12; 2021-06-14: 14; 2021-07-12: 12; 2021-08-16: 17; 2021-09-13: 14; 2021-10-11: 12; 2021-11-08: 12; 2021-12-13: 14; 2022-01-17: 17; 2022-02-07: 12; 2022-03-14: 14
310 | • | Payroll: salaries paid, ledger | Month | 25/x | Accounts | Staff | 2021-04-19: 23; 2021-05-24: 25; 2021-06-21: 25; 2021-07-19: 25; 2021-08-23: 25; 2021-09-20: 24; 2021-10-25: 25; 2021-11-22: 25; 2021-12-20: 23; 2022-01-24: 25; 2022-02-21: 25; 2022-03-21: 25
311 | • | Vendor information: FORA, … | Annum | Jan | Accounts | Vendor | bar: 2022-01-24
312 | • | Statement of earnings & deductions KU10 + SKV2304, if dividend | Annum | Jan | Accounts | Skatteverket
313 | • | Close year and annual report | Annum | FYE | Accounts | Board, Skatteverket, BV? | 2021-10-18: 18
314 |  | - Request engagemengsrapport from bank | bar: 2021-03-29 to 2021-04-26
315 |  | - Skattekonto utdrag, MOMS & AGI sammanställning FY |  |  |  |  | 2021-12-06: 7
316 |  | - Beslut debiterad prelskatt FY |  |  |  |  | 2021-12-06: 7
317 |  | - Accrual for sales and vendor purchase orders | bar: 2021-03-29 to 2021-04-26
318 |  | - Förvaltningsberättelse |  |  |  |  | 2021-10-18: 18
319 |  | - Annual report sign and submit to BV |  |  |  |  | 2021-08-09: 10; 2021-10-18: 18
320 | • | Dun unpaid invoices | Month | +1w | Accounts | Customer A/R | bar: 2021-03-29 to 2021-04-05; 2021-04-26 to 2021-05-03; 2021-05-31; 2021-07-05; 2021-08-02; 2021-08-30; 2021-10-04; 2021-11-08; 2021-11-29 to 2021-12-06; 2022-01-03; 2022-01-31; 2022-02-28
321 | • | Pay contractors when invoice payment received, update PastDue | Month | +5d | Accounts | Vendor A/P | 2021-08-09: NFA; 2022-02-07: 8
322 | • | Produce reports: balance sheet, income statement (P/L), A/R, A/P. | Quarter | w1 | Accounts | Accountant, Board | 2021-10-18: 18; 2021-12-06: 7; 2022-03-07: 8
323 | • | Tax return - inkomstdeklaration 2 för räkenskapsåretslut 20200331 | Annum |  | Accounts |  | 2021-10-18: 18
324 | • | Archive verifications for previous year and start new binder. | Annum | bar: 2021-03-29
325 | • | Create archive folder for previous FY: AR, AP, Bank, Comptrol, Time reporting, vendor PO, Taxation, Payroll, Budget | Annum | bar: 2021-03-29
326 | • | Update KYC at bank | Annum |  | Accounts | Bank | bar: 2022-03-28
300 | Financial
401 | • | Sales Account Planning
402 | • | Business Targets
403 | • | Sales Review
110 | • | Move opportunities into sales funnel for new FY | Annum | bar: 2021-03-29
400 | Sales
501 | • | Time reporting | Week |  |  |  | 2021-03-29: 31; 2021-04-26: 30; 2021-05-24: B3; 2021-05-31: 31; 2021-06-21: B3; 2021-06-28: 30; 2021-07-19: B3; 2021-07-26: 31; 2021-08-23: B3; 2021-08-30: 31; 2021-09-20: B3; 2021-09-27: 30,3; 2021-10-25: 29,31; 2021-11-22: 28; 2021-11-29: 30; 2021-12-20: 22,23; 2022-01-24: 28; 2022-01-31: 31; 2022-02-21: 26; 2022-02-28: 28; 2022-03-21: 26; 2022-03-28: 31
502 | • | Create resource map for next CY | Annum | bar: 2021-12-20
503 | • | Create annual plan for new FY | Annum | bar: 2021-03-29; 2022-02-28
504 | • | Create new management action log for CY and move open actions | Annum | bar: 2021-12-20
505 | • | Create document register for new CY | Annum | bar: 2021-12-20
506 | • | Review and update office handbook | Annum | bar: 2021-12-20
507 | • | Generate, proofread and cut all planR calendars | Annum | bar: 2021-11-01 to 2021-11-22
508 | • | Customer survey | Biannual | Jun, Dec | COO | Customers | 2021-07-12: Inera; 2021-08-02: PL; 2021-08-09: Inera; 2021-12-06: Dun
509 | • | Staff survey | Biannual | Jun, Dec | COO | Contractors | 2021-12-27: Per
510
511
500 | Operations

## FY2023 (hidden)
No. | Activities | [5 empty] | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4
|  |  | Per | Timing | Responsible | Receiver(s) | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  |  | March
[7 empty] | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
CET | time axis 2023-04-03 to 2024-03-25
101 | • | Call to Ordinary Annual General Meeting (4-6 weeks prior) - agenda | Annum | 4-6w prior | Board | Shareholders | bar: 2023-04-17
102 | • | Annual General Meeting (ordinary) | Annum | < 6 m EOFY | Chairperson | Shareholders | 2023-05-08: 9
103 | • | AGM Minutes of Meeting | Annum | within 2 w | Chairperson | Shareholders, on request | 2023-05-08: 9
104 | • | Call to Board Meeting | Quarter | 7d prior | Chairperson, MD | Board of Directors, MD | 2023-05-08: 9
105 | • | Review and update charter for Board of Directors (1) | Annum |  | Board | Board of Directors
106 | • | Review and update charter for Managing Director (1) | Annum |  | Board | Board of Directors
107 | • | Generate and analyse metrics for annual report | Annum |  | MD | Board of Directors | bar: 2023-05-08
108 | • | Budget proposal (1) | Annum |  | MD | Board of Directors | 2023-05-08: 11
109 | • | Business Plan | Annum |  | MD | Board of Directors | 2023-05-08: 11
110 | • | Board Meeting | Quarter | Ju, Se, De, Ma | Chairperson | Board of Directors, MD | 2023-05-15: 15; 2023-09-04: 6; 2023-12-11: 15; 2024-03-04: 5
111 | • | Board Meeting Minutes of Meeting | Quarter | > 7d prior |  | Board of Directors, MD | 2023-05-15: 15; 2023-09-04: 6; 2023-12-11: 15; 2024-03-04: 5
100 | Shareholders / Board of Directors
201 | • | Book end of year party | Annum | bar: 2023-09-04
202 | • | End of year party | Annum |  |  |  | 2023-12-11: 15
203 | • | Performance Appraisal | Biannual
204 | • | Consultancy profile (start, end assignment, sales cycle) | Annum
205 | • | Update the Personal Information File | Annum
206 | • | Create staff register for new CY | Annum | bar: 2024-01-01
207 | • | Create archive folders for Recruitment | Annum | bar: 2024-01-01
200 | Human Resources
300 | • | Book-keeping: reconcile bank transactions | Day/week |  | Accounts |  | 2023-04-03: 6; 2023-05-08: 9
301 | • | Book-keeping: review G/L accounts, close month. | Month | 1/x? | Accounts | Accountant | 2023-05-08: 9; 2023-06-05: 8; 2023-08-07: 8; 2023-09-04: 5; 2023-10-02: 3; 2023-11-06: 7; 2023-12-04: 7; 2024-01-08: 9; 2024-02-05: 6; 2024-03-04: 5
302 | • | European VAT Summary | Quarter |  |  |  | 2023-04-03: 6; 2023-08-07: 8; 2023-10-02: 3; 2024-02-05: 6
303 | • | End of month report: actual V budget | Month | 15/x | Accounts | MD | 2023-05-08: 9; 2023-06-05: 8; 2023-08-07: 8; 2023-09-04: 5; 2023-10-02: 3; 2023-11-06: 7; 2023-12-04: 7; 2024-01-08: 9; 2024-02-05: 6; 2024-03-04: 5
304 | • | Vendor invoicing: create, invoice/receipt, VAT, bank payment | Day |  | Accounts
305 | • | Sales invoicing: time reporting, ledger, deliver, VAT, enter PastDue | Month | 31/x | Accounts | Customer A/R | 2023-04-24: 28; 2023-05-22: 26; 2023-05-29: 31; 2023-06-19: 23; 2023-06-26: 30; 2023-07-24: 28; 2023-07-31: 31; 2023-08-21: 25; 2023-08-28: 31; 2023-09-25: 29; 2023-10-23: 27; 2023-10-30: 31; 2023-11-20: 24; 2023-11-27: 30; 2023-12-18: 22; 2023-12-25: 29; 2024-01-22: 26; 2024-01-29: 31; 2024-02-19: 23; 2024-02-26: 29; 2024-03-25: 28
306 | • | Payroll: payslips, bank payment, tax report, tax declaration | Month | 20/x | HR, Accounts | Staff, Skatteverket | 2023-04-17: 20; 2023-05-15: 19; 2023-06-19: 20; 2023-07-17: 20; 2023-08-14: 18; 2023-09-18: 20; 2023-10-16: 20; 2023-11-20: 20; 2023-12-18: 20, 21; 2024-01-15: 20; 2024-02-19: 20; 2024-03-18: 20
307 | • | VAT declaration | Quarter | Q+1+12 | Accounts | Skatteverket | 2023-08-07: 8; 2023-11-13: 13; 2024-02-12: 12
308 | • | Tax bank payment to Skatteverket (payrollx2, corp, VAT) | Month |  | Accounts | Skatteverket | 2023-04-03: 6; 2023-06-05: 8; 2023-07-10: 10; 2023-08-07: 8; 2023-09-04: 5; 2023-10-09: 2; 2023-11-13: 13; 2024-01-08: 9
309 | • | Tax withdrawals. Ledger to/from SV (corp, payroll, VAT) | Month | +12 | Accounts | Skatteverket | 2023-04-10: 12; 2023-05-08: 12; 2023-06-12: 12; 2023-07-10: 12; 2023-08-14: 14; 2023-09-11: 12; 2023-10-09: 12; 2023-11-13: 13; 2024-01-08: 12; 2024-02-12: 12; 2024-03-11: 12
310 | • | Book preliminary tax withdrawal for tax account (and interest) | Month | +12 |  |  | 2023-04-10: 12; 2023-05-08: 12; 2023-06-12: 12; 2023-07-10: 13; 2023-08-14: 15; 2023-09-11: 13; 2023-10-09: 13; 2023-11-13: 14; 2024-01-15: 15; 2024-02-12: 13; 2024-03-11: 13
311 | • | Payroll: salaries paid, ledger | Month | 25/x | Accounts | Staff | 2023-04-24: 25; 2023-05-22: 25; 2023-06-19: 22; 2023-07-24: 25; 2023-08-21: 25; 2023-09-25: 25; 2023-10-23: 25; 2023-11-20: 25; 2023-12-18: 22; 2024-01-22: 25; 2024-02-19: 25; 2024-03-25: 25
312 | • | Payroll review (based on tax rates) | Annum | Jan | MD | Staff | 2024-01-08: 9
313 | • | Vendor information: FORA, … | Annum | Jan | Accounts | Vendor | bar: 2024-02-05
314 | • | Statement of earnings & deductions KU10 + SKV2304, if dividend | Annum | Jan | Accounts | Skatteverket
315 | • | Close year and annual report | Annum | FYE | Accounts | Board, Skatteverket, BV? | bar: 2023-05-08
316 |  | - Request engagemengsrapport from bank | bar: 2023-04-03
317 |  | - Skattekonto utdrag, MOMS & AGI sammanställning FY | bar: 2023-05-01
318 |  | - FY Bank transactions PDF & CDF | bar: 2023-04-03
319 |  | - Beslut debiterad prelskatt FY |  |  |  |  | 2023-04-03: 6
320 |  | - Accrual for sales and vendor purchase orders | bar: 2023-04-03
321 |  | - Förvaltningsberättelse | bar: 2023-05-08
322 |  | - Annual report sign and submit to BV | bar: 2023-05-08
323 | • | Set preliminärskatt level for new FY | Annum | May | Accounts | Skatteverket | bar: 2023-04-03
324 | • | Dun unpaid invoices | Month | +1w | Accounts | Customer A/R | bar: 2023-04-03; 2023-05-01; 2023-06-05; 2023-07-03; 2023-07-31; 2023-10-02; 2023-10-30; 2023-12-04; 2024-01-01; 2024-02-05; 2024-03-04
325 | • | Pay contractors when invoice payment received, update PastDue | Month | +5d | Accounts | Vendor A/P | 2024-01-08: 9
326 | • | Produce reports: balance sheet, income statement (P/L), A/R, A/P. | Quarter | w1 | Accounts | Accountant, Board | 2023-12-11: 13
327 | • | Tax return - inkomstdeklaration 2 för räkenskapsåretslut 20200331 | Annum |  | Accounts |  | 2023-10-02: 3
328 | • | Archive verifications for previous year and start new binder. | Annum | bar: 2023-04-03
329 | • | Create archive folder for previous FY: AR, AP, Bank, Comptrol, Time reporting, vendor PO, Taxation, Payroll, Budget | Annum | bar: 2023-04-03
330 | • | Update KYC at bank | Annum |  | Accounts | Bank
300 | Financial
401 | • | Sales Account Planning
402 | • | Business Targets
403 | • | Sales Review
110 | • | Move opportunities into sales funnel for new FY | Annum | bar: 2023-04-03
400 | Sales
501 | • | Time reporting | Week |  |  |  | 2023-04-24: 28; 2023-05-22: 26; 2023-05-29: 31; 2023-06-19: 23; 2023-06-26: 30; 2023-07-24: 28; 2023-07-31: 31; 2023-08-21: 25; 2023-08-28: 31; 2023-09-18: 22; 2023-09-25: 29; 2023-10-23: 27; 2023-10-30: 31; 2023-11-20: 24; 2023-11-27: 30; 2023-12-18: 22; 2023-12-25: 29; 2024-01-22: 26; 2024-01-29: 31; 2024-02-19: 23; 2024-02-26: 29; 2024-03-18: 22; 2024-03-25: 29
502 | • | Create resource map for next CY | Annum | bar: 2023-10-30
503 | • | Create annual plan for new FY | Annum | bar: 2023-12-18
504 | • | Create new management action log for CY and move open actions | Annum | bar: 2023-12-04
505 | • | Create document register for new CY | Annum | bar: 2023-12-04
506 | • | Review and update office handbook | Annum
507 | • | Generate, proofread and cut all planR calendars | Annum | bar: 2023-10-30
508 | • | Customer survey | Biannual | Jun, Dec | COO | Customers
509 | • | Staff survey | Biannual | Jun, Dec | COO | Contractors
510 | • | Book monthly operations meetings 6 months ahead | bar: 2023-06-05; 2023-11-27
511 | • | Create time reporting for next year - consultants, services | bar: 2023-10-30
512 | • | Create cash flow for next FY | bar: 2024-01-01
513 | •
500 | Operations

## FY2024 (hidden)
No. | Activities | [5 empty] | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4
|  |  | Per | Timing | Responsible | Receiver(s) | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  |  | March
[7 empty] | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
CET | time axis 2024-04-01 to 2025-03-24
101 | • | Call to Ordinary Annual General Meeting (4-6 weeks prior) - agenda | Annum | 4-6w prior | Board | Shareholders | bar: 2024-05-13; 2025-03-10
102 | • | Annual General Meeting (ordinary) | Annum | < 6 m EOFY | Chairperson | Shareholders | 2024-05-20: 21
103 | • | AGM Minutes of Meeting | Annum | within 2 w | Chairperson | Shareholders, on request | 2024-05-20: 21
104 | • | Call to Board Meeting | Quarter | 7d prior | Chairperson, MD | Board of Directors, MD | bar: 2024-05-13; 2024-12-02 to 2024-12-09; 2025-03-10
105 | • | Review and update charter for Board of Directors (1) | Annum |  | Board | Board of Directors | bar: 2025-03-03
106 | • | Review and update charter for Managing Director (1) | Annum |  | Board | Board of Directors | bar: 2025-03-03
107 | • | Generate and analyse metrics for annual report | Annum |  | MD | Board of Directors | bar: 2024-05-13
108 | • | Budget | Annum |  | MD | Board of Directors | bar: 2025-03-10
109 | • | Business Plan | Annum |  | MD | Board of Directors | bar: 2025-03-10
110 | • | Board Meeting | Quarter | Ju, Se, De, Ma | Chairperson | Board of Directors, MD | 2024-05-20: 24; 2024-09-16: 18; 2024-12-09: 11; 2025-03-10: 10
111 | • | Board Meeting Minutes of Meeting | Quarter | > 7d prior |  | Board of Directors, MD | 2024-05-20: 24; 2024-09-16: 19; 2024-12-09: 11; 2025-03-10: 10
100 | Shareholders / Board of Directors
201 | • | Book end of year party | Annum | bar: 2024-08-12
202 | • | End of year party | Annum |  |  |  | 2024-12-09: 10
203 | • | Performance Appraisal | Biannual
204 | • | Consultancy profile (start, end assignment, sales cycle) | Annum
205 | • | Update the Personal Information File | Annum
206 | • | Create staff register for new CY | Annum | bar: 2024-12-30
207 | • | Create archive folders for Recruitment | Annum
200 | Human Resources
300 | • | Book-keeping: reconcile bank transactions | Day/week |  | Accounts
301 | • | Book-keeping: review G/L accounts, close month. | Month | 1/x? | Accounts | Accountant | 2024-04-08: 10; 2024-05-06: 7; 2024-06-03: 5; 2024-07-01: 3; 2024-08-05: 6; 2024-09-02: 4; 2024-10-07: 8; 2024-11-04: 5; 2024-12-09: 9; 2025-01-06: 7; 2025-02-03: 5; 2025-03-03: 5
302 | • | European VAT Summary | Quarter |  |  |  | 2024-04-08: 10; 2024-07-01: 3; 2024-10-07: 8; 2025-01-06: 7
303 | • | End of month report: actual V budget | Month | 15/x | Accounts | MD | 2024-04-08: 10; 2024-05-06: 7; 2024-06-03: 5; 2024-07-01: 3; 2024-09-02: 4; 2024-10-07: 8; 2024-11-04: 5; 2024-12-09: 9; 2025-01-06: 7; 2025-02-03: 5; 2025-03-03: 5
304 | • | Check new tabellskatt 31 at SKV | bar: 2024-12-30
305 | • | Vendor invoicing: create, invoice/receipt, VAT, bank payment | Day |  | Accounts
306 | • | Sales invoicing: time reporting, ledger, deliver, VAT, enter PastDue | Month | 31/x | Accounts | Customer A/R | 2024-04-22: 26; 2024-04-29: 30; 2024-05-20: 24; 2024-05-27: 31; 2024-06-17: 20; 2024-06-24: 28; 2024-07-22: 26; 2024-07-29: 31; 2024-08-19: 23; 2024-08-26: 31; 2024-09-16: 20; 2024-09-30: 30; 2024-10-21: 25; 2024-10-28: 31; 2024-11-18: 22; 2024-11-25: 29; 2024-12-16: 20; 2024-12-30: 30; 2025-01-20: 24; 2025-01-27: 31; 2025-02-24: 28; 2025-03-24: x
307 | • | Payroll: payslips, bank payment, tax report, tax declaration (even if zero salary) | Month | 20/x | HR, Accounts | Staff, Skatteverket | 2024-04-15: 20; 2024-05-20: 20; 2024-06-17: 20; 2024-07-15: 20; 2024-08-19: 20; 2024-09-16: 20; 2024-10-14: 20; 2024-11-18: 20; 2024-12-16: 20; 2025-01-20: 20; 2025-02-17: 20; 2025-03-17: 20
308 | • | VAT declaration | Quarter | Q+1+12 | Accounts | Skatteverket | 2024-05-06: 7; 2024-11-04: 5; 2025-02-03: 5
309 | • | Tax bank payment to Skatteverket (payrollx2, corp, VAT) | Month |  | Accounts | Skatteverket | 2024-04-08: 10; 2024-05-06: 7; 2024-06-03: 5; 2024-07-01: 3; 2024-09-02: 4; 2024-10-07: 8; 2024-11-04: 5; 2024-12-09: 9; 2025-01-06: 7; 2025-02-03: 5; 2025-03-03: 5
310 | • | Tax withdrawals. Ledger to/from SV (corp, payroll, VAT) | Month | +12 | Accounts | Skatteverket | 2024-04-08: 12; 2024-05-13: 13; 2024-06-10: 12; 2024-07-08: 12; 2024-08-19: 19; 2024-09-09: 12; 2024-10-14: 14; 2024-11-11: 12; 2024-12-09: 12; 2025-01-13: 17; 2025-02-10: 12; 2025-03-10: 12
311 | • | Book preliminary tax withdrawal for tax account | Month | +12 |  |  | 2024-04-15: 15; 2024-05-13: 13; 2024-06-10: 13; 2024-07-08: 13; 2024-08-19: 20; 2024-09-09: 13; 2024-10-14: 15; 2024-11-11: 13; 2024-12-09: 13; 2025-01-20: 20; 2025-02-10: 13; 2025-03-10: 13
312 | • | Payroll: salaries paid, ledger | Month | 25/x | Accounts | Staff | 2024-04-22: 25; 2024-05-20: 24; 2024-06-24: 25; 2024-07-22: 25; 2024-08-19: 25; 2024-09-23: 25; 2024-10-21: 25; 2024-11-25: 25; 2024-12-23: 25; 2025-01-20: 24; 2025-02-24: 25; 2025-03-24: 25
313 | • | Payroll review (based on tax rates) | Annum | Jan | MD | Staff | 2025-01-06: 7; 2025-02-03: 5
314 | • | Vendor information: FORA, … | Annum | Jan | Accounts | Vendor
315 | • | Statement of earnings & deductions KU10 + SKV2304, if dividend | Annum | Jan | Accounts | Skatteverket
316 | • | Close year and annual report | Annum | FYE | Accounts | Board, Skatteverket, BV? | 2024-05-13: 13; 2024-05-20: 20
317 | • | Produce reports: balance sheet, income statement (P/L), A/R, A/P. | Quarter | w1 | Accounts | Accountant, Board | bar: 2024-05-20
318 |  | - Skattekonto utdrag, MOMS & AGI sammanställning FY |  |  |  |  | 2024-05-20: 20
319 |  | - Förvaltningsberättelse |  |  |  |  | 2024-05-20: 20
320 |  | - Annual report sign and submit to BV |  |  |  |  | 2024-05-20: 20
321 |  | - Request engagemengsrapport from bank | bar: 2024-04-01
322 |  | - FY Bank transactions PDF & CSV | bar: 2024-04-01
323 |  | - Beslut debiterad prelskatt FY | bar: 2024-04-08
324 |  | - Accrual for sales and vendor purchase orders |  |  |  |  | 2024-04-08: 10
325 | • | Set preliminärskatt level for new FY | Annum | May | Accounts | Skatteverket | bar: 2024-05-06
326 | • | Archive verifications for previous year and start new binder. | Annum | bar: 2024-04-22
327 | • | Create archive folder for previous FY: AR, AP, Bank, Comptrol, Time reporting, vendor PO, Taxation, Payroll, Budget | Annum | bar: 2024-04-22
328 | • | Calculate compound interest, and book in Visma | Quarter | w +1 | Accounts | Skatteverket
329 | • | Update KYC at bank | Annum |  | Accounts | Bank
330 | • | Dun unpaid invoices | Month | +1w | Accounts | Customer A/R | bar: 2024-04-01; 2024-05-06; 2024-06-03; 2024-07-01; 2024-07-29; 2024-09-02; 2024-09-30; 2024-11-04; 2024-12-02; 2025-02-03; 2025-03-03
331 | • | Pay contractors when invoice payment received, update PastDue | Month | +5d | Accounts | Vendor A/P | bar: 2024-04-01 to 2024-04-08; 2024-05-06; 2024-06-03; 2024-07-01 to 2024-07-08; 2024-07-29 to 2024-08-05; 2024-09-02 to 2024-09-09; 2024-09-30 to 2024-10-07; 2024-11-04; 2024-12-02; 2025-01-06; 2025-02-03; 2025-03-03 to 2025-03-10
332 | • | Tax return - inkomstdeklaration 2 för räkenskapsåretslut 202x0331 | Annum |  | Accounts | bar: 2024-09-09 to 2024-10-07
300 | Financial
401 | • | Sales Account Planning
402 | • | Business Targets
403 | • | Sales Review
110 | • | Move opportunities into sales funnel for new FY | Annum | bar: 2024-04-01
400 | Sales
501 | • | Time reporting | Week |  |  |  | 2024-04-22: 26; 2024-04-29: 30; 2024-05-20: 24; 2024-05-27: 31; 2024-06-17: 20; 2024-06-24: 28; 2024-07-22: 26; 2024-07-29: 31; 2024-08-19: 23; 2024-08-26: 31; 2024-09-16: 20; 2024-09-30: 30; 2024-10-21: 25; 2024-10-28: 31; 2024-11-18: 22; 2024-11-25: 29; 2024-12-16: 20; 2024-12-30: 30; 2025-01-20: 24; 2025-01-27: 31; 2025-02-24: 28; 2025-03-24: x
502 | • | Create resource map for next CY | Annum | bar: 2024-11-04
503 | • | Create annual plan for new FY | Annum | bar: 2025-03-03
504 | • | Create new management action log for CY and move open actions | Annum | bar: 2024-12-23
505 | • | Create document register for new CY | Annum | bar: 2024-11-25
506 | • | Review and update office handbook | Annum
507 | • | Generate, proofread and cut all planR calendars | Annum | bar: 2024-11-04
508 | • | Customer survey | Biannual | Jun, Dec | COO | Customers
509 | • | Staff survey | Biannual | Jun, Dec | COO | Contractors
510 | • | Book monthly operations meetings 6 months ahead
511 | • | Create time reporting for next year - consultants, services | bar: 2024-11-04
512 | • | Create cash flow for next FY | bar: 2024-12-30
513 | • | Backup | bar: 2024-11-25; 2024-12-30; 2025-01-27; 2025-02-17; 2025-03-24
500 | Operations

## FY2022 (hidden)
No. | Activities | [5 empty] | Q1 | [13 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4
|  |  | Per | Timing | Responsible | Receiver(s) | April |  |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March
[7 empty] | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
CET | time axis 2022-03-28 to 2023-03-27
101 | • | Call to Ordinary Annual General Meeting (4-6 weeks prior) - agenda | Annum | 4-6w prior | Board | Shareholders
102 | • | Annual General Meeting (ordinary) | Annum | < 6 m EOFY | Chairperson | Shareholders | 2022-04-11: 13
103 | • | AGM Minutes of Meeting | Annum | within 2 w | Chairperson | Shareholders, on request
104 | • | Call to Board Meeting | Quarter | 7d prior | Chairperson, MD | Board of Directors, MD | bar: 2022-04-11; 2023-02-27
105 | • | Review and update charter for Board of Directors (1) | Annum |  | Board | Board of Directors | bar: 2022-04-11
106 | • | Review and update charter for Managing Director (1) | Annum |  | Board | Board of Directors | bar: 2022-04-11
107 | • | Generate and analyse metrics for annual report | Annum |  | MD | Board of Directors | bar: 2022-04-11
108 | • | Budget proposal (1) | Annum |  | MD | Board of Directors | 2022-05-09: 10
109 | • | Business Plan | Annum |  | MD | Board of Directors | 2022-05-09: 10
110 | • | Board Meeting | Quarter | Ju, Se, De, Ma | Chairperson | Board of Directors, MD | 2022-05-09: 11; 2022-09-05: 6; 2022-12-19: 19; 2023-03-13: 13
111 | • | Board Meeting Minutes of Meeting | Quarter | > 7d prior |  | Board of Directors, MD | 2022-05-09: 12; 2022-12-19: 20
100 | Shareholders / Board of Directors
201 | • | Book end of year party | Annum | bar: 2022-10-10 to 2022-10-17
202 | • | End of year party | Annum |  |  |  | 2022-12-19: 19
203 | • | Performance Appraisal | Biannual | bar: 2022-06-27
204 | • | Consultancy profile (start, end assignment, sales cycle) | Annum | bar: 2022-06-27; 2022-12-12
205 | • | Update the Personal Information File | Annum | bar: 2022-06-27; 2022-12-12
206 | • | Create staff register for new CY | Annum | bar: 2022-12-26
207 | • | Create archive folders for Recruitment | Annum
200 | Human Resources
300 | • | Book-keeping: reconcile bank transactions | Day/week |  | Accounts |  | 2023-01-09: 9
301 | • | Book-keeping: review G/L accounts, close month. | Month | 1/x? | Accounts | Accountant | 2022-04-04: 5; 2022-05-09: 10; 2022-06-06: 7; 2022-08-08: 9; 2022-09-05: 5; 2022-10-10: 10; 2022-11-07: 7; 2022-12-05: 5; 2023-01-09: 9; 2023-02-06: 6; 2023-03-06: 6
302 | • | European VAT Summary | Quarter |  |  |  | 2022-10-10: 10; 2023-01-09: 9; 2023-02-06: 6; 2023-03-06: 6
303 | • | End of month report: actual V budget | Month | 15/x | Accounts | MD | 2022-04-04: 5; 2022-05-09: 10; 2022-06-06: 7; 2022-10-10: 10; 2023-01-09: 9; 2023-02-06: 6; 2023-03-06: 6
304 | • | Vendor invoicing: create, invoice/receipt, VAT, bank payment | Day |  | Accounts
305 | • | Sales invoicing: time reporting, ledger, deliver, VAT, enter PastDue | Month | 31/x | Accounts | Customer A/R | 2022-04-25: 30; 2022-05-23: 27; 2022-05-30: 31; 2022-06-20: 23; 2022-06-27: 30; 2022-07-25: 29; 2022-08-22: 26; 2022-08-29: 31; 2022-09-19: 23; 2022-09-26: 30; 2022-10-24: 28; 2022-10-31: 31; 2022-11-21: 25; 2022-11-28: 30; 2022-12-19: 23; 2022-12-26: 30; 2023-01-23: 27; 2023-01-30: 31; 2023-02-20: 24; 2023-02-27: 28; 2023-03-20: 24; 2023-03-27: 31
306 | • | Payroll: payslips, bank payment, tax report, tax declaration | Month | 20/x | HR, Accounts | Staff, Skatteverket | 2022-04-18: 20; 2022-06-20: 20; 2022-07-18: 20; 2022-08-15: 19; 2022-09-19: 20; 2022-10-17: 20; 2022-11-21: 21; 2022-12-19: 19; 2023-01-16: 20; 2023-02-20: 20; 2023-03-20: 20
307 | • | VAT declaration | Quarter | Q+1+12 | Accounts | Skatteverket | 2022-05-09: 10; 2022-08-08: 9; 2022-11-07: 7; 2023-02-06: 6
308 | • | Tax bank payment to Skatteverket (payrollx2, corp, VAT) | Month |  | Accounts | Skatteverket | 2022-04-04: 5; 2022-05-09: 10; 2022-06-06: 7; 2022-08-08: 9; 2022-09-05: 9; 2022-10-10: 10; 2022-11-07: 7; 2023-01-09: 9; 2023-02-06: 6; 2023-03-06: 6
309 | • | Tax withdrawals. Ledger to/from SV (corp, payroll, VAT) | Month | +12 | Accounts | Skatteverket | 2022-04-11: 12; 2022-05-09: 12; 2022-06-13: 13; 2022-07-11: 12; 2022-08-15: 17; 2022-09-12: 12; 2022-10-10: 12; 2022-11-14: 14; 2022-12-12: 12; 2023-02-06: 9; 2023-03-13: 13
310 | • | Payroll: salaries paid, ledger | Month | 25/x | Accounts | Staff | 2022-04-25: 25; 2022-05-23: 25; 2022-06-20: 23; 2022-07-25: 25; 2022-09-19: 23; 2022-10-24: 25; 2022-11-21: 25; 2022-12-19: 22; 2023-01-23: 25; 2023-02-20: 24
311 | • | Payroll review | Annum | Jan | MD | Staff | bar: 2023-01-02 to 2023-01-23
312 | • | Vendor information: FORA, … | Annum | Jan | Accounts | Vendor | bar: 2023-01-02
313 | • | Statement of earnings & deductions KU10 + SKV2304, if dividend | Annum | Jan | Accounts | Skatteverket | 2023-01-09: 9
314 | • | Close year and annual report | Annum | FYE | Accounts | Board, Skatteverket, BV? | 2022-04-11: 13
315 |  | - Request engagemengsrapport from bank | bar: 2022-04-04
316 |  | - Skattekonto utdrag, MOMS & AGI sammanställning FY |  |  |  |  | 2022-04-11: 13
317 |  | - Beslut debiterad prelskatt FY |  |  |  |  | 2022-04-11: 13
318 |  | - Accrual for sales and vendor purchase orders | bar: 2022-04-04
319 |  | - Förvaltningsberättelse |  |  |  |  | 2022-04-11: 13
320 |  | - Annual report sign and submit to BV |  |  |  |  | 2022-04-11: 13
321 | • | Set preliminärskatt level for new FY | Annum | May | Accounts | Skatteverket | bar: 2022-04-04
322 | • | Dun unpaid invoices | Month | +1w | Accounts | Customer A/R | bar: 2022-04-25; 2022-05-30; 2022-07-04 to 2022-07-11; 2022-08-01; 2022-08-29 to 2022-09-05; 2022-10-03; 2022-10-31; 2022-11-28 to 2022-12-05; 2023-01-02; 2023-01-30; 2023-02-27
323 | • | Pay contractors when invoice payment received, update PastDue | Month | +5d | Accounts | Vendor A/P | bar: 2022-04-25 to 2022-05-02; 2022-05-30; 2022-07-04 to 2022-07-11; 2022-08-01; 2022-08-29 to 2022-09-05; 2022-10-03; 2022-10-31; 2022-11-28 to 2022-12-05; 2023-01-02; 2023-01-30; 2023-02-27
324 | • | Produce reports: balance sheet, income statement (P/L), A/R, A/P. | Quarter | w1 | Accounts | Accountant, Board | 2022-05-09: 10
325 | • | Tax return - inkomstdeklaration 2 för räkenskapsåretslut 20200331 | Annum |  | Accounts | bar: 2022-08-29
326 | • | Archive verifications for previous year and start new binder. | Annum | bar: 2022-04-04
327 | • | Create archive folder for previous FY: AR, AP, Bank, Comptrol, Time reporting, vendor PO, Taxation, Payroll, Budget | Annum | bar: 2022-04-04
328 | • | Update KYC at bank | Annum |  | Accounts | Bank | bar: 2022-04-04
300 | Financial
401 | • | Sales Account Planning
402 | • | Business Targets
403 | • | Sales Review
110 | • | Move opportunities into sales funnel for new FY | Annum | bar: 2022-04-04
400 | Sales
501 | • | Time reporting | Week |  |  |  | 2022-04-25: 30; 2022-05-23: 27; 2022-05-30: 31; 2022-06-20: 23; 2022-06-27: 30; 2022-07-25: 29; 2022-08-22: 26; 2022-08-29: 31; 2022-09-19: 23; 2022-09-26: 30; 2022-10-24: 28; 2022-10-31: 31; 2022-11-21: 25; 2022-11-28: 30; 2022-12-19: 23; 2022-12-26: 30; 2023-01-23: 27; 2023-01-30: 31; 2023-02-20: 24; 2023-02-27: 28; 2023-03-20: 24
502 | • | Create resource map for next CY | Annum | bar: 2022-12-19
503 | • | Create annual plan for new FY | Annum | bar: 2022-03-28; 2023-01-30
504 | • | Create new management action log for CY and move open actions | Annum | bar: 2022-12-19
505 | • | Create document register for new CY | Annum | bar: 2022-12-19
506 | • | Review and update office handbook | Annum | bar: 2022-12-19
507 | • | Generate, proofread and cut all planR calendars | Annum
508 | • | Customer survey | Biannual | Jun, Dec | COO | Customers | bar: 2022-06-27 to 2022-07-11; 2022-08-15 to 2022-08-22
509 | • | Staff survey | Biannual | Jun, Dec | COO | Contractors | bar: 2022-06-27 to 2022-07-11
510
511
500 | Operations

## Instructions
Annual Plan |  | PF/O-26:002 2026-03-06 version 2.0.0
A template for co-ordinating key events, commitments, and interactions across a company.
Introduction
Have you ever witnessed the surprise and panic when annual budgeting and performance appraisals are due, despite taking place at the same time every year?
The annual plan needs to exist at the company level, enabling all parts to synchronise around major events, interactions, and mutual obligations.
The benefits are immediate and significant: managers can prepare, be punctual, and also plan their own work in the confidence that it won't be sabotaged by external important and urgent obligations. The aim is to synchronise the company so that each division or part can plan and perform their work without being surprised by regular, fixed events.
Configuration
At the beginning of each year it needs to be modified and set up for the new financial year, but the advantages far outweigh that minor administration. Follow these steps to tailor the template to your needs, and to be used in a new financial year.
• Set the date in Cell H4 to the Monday of the week which contains the first day of your financial year. N.B. entering the date will follow the format mm/dd/yy, regardless of how it is displayed in the cell. E.g. If financial year starts 1st Jan, in 2026 that day falls on Thursday of week 1, and week 1 2026 has its Monday on 29th Dec.
• Some years have 53 weeks. Insert week columns where necessary to ensure that you include weeks for 1st January and 31st December. Tip: insert columns inside the table to maintain same data and formatting.
• The number of weeks in a month varies from year to year. I count how many weekdays are in each month, and move it to the month where most days fall.
N.B. When you move weeks into other months, you will also need to modify the border of the Month, and Quarter to match.
• There are six sections in this template, representing six major parts of a company. Rename and add sections to represent all the functions in your company. N.B. I include a section for shareholders and members of the board, which is beyond the operations of the company, but it is good for everyone including the CEO to see the overall alignment between functions.
Using the Annual Plan
A - Decide which events to plan
The most difficult part is deciding which events are important enough to plan. The fewer the better. We want to show the necessary and sufficient events, and not drown in information.
Column | Description | Usage
C - Events | The list of major events, interactions, and obligations across the company, divided into sections representing each function, division, or department. | Do not go into too much detail; use the following criteria as a guide:- • Do other divisions/departments need to know about this event? That is, do they contribute, and need to know when this occurs? • Do I need to announce that I have a fixed commitment at this date, which blocks our availability for other considerations? • Is this event/work fixed and regular? That is, everyone benefits by knowing this is advance.
D - Per | The frequency of the event. | How often is it today? Is it too often, or need to be more often? As this is supposed to be major cross-company co-ordination, question whether weekly or shorter should be in the plan.
E - Timing | The constraints that need to be considered when scheduling this event. | e.g. Company bylaws might specify that the invitation for a board meeting and all supporting documentation must be made 30 days prior to the meeting. Nevertheless, it is common to get the information the night before, so no-one can be prepared for the meeting. If the week of the board meeting is fixed, this will never be an issue.
F - Responsible | The role in the company which is responsible for this event taking place, and approving the schedule.
G - Receiver(s) | Shows who is directly affected by this event.
N.B. Once this section is completed and all events have been planned for the year, columns D-G can be collapsed to reduce clutter.
B - Annual Planning
The annual planning happens in the calendar section (columns H-BH) of the template. The explanation will use the following example:-
• In row 4, the date will automatically turn from green to yellow once the week has passed. In this example, the columns for January and February can now be hidden to reduce clutter.
• Following the conventions of a Gantt chart, planning is denoted by blue cells.
• The plan can be that the event will take place within a period (e.g. 101), within a week (e.g. 103), or on a specific date (e.g. 104). The more specific a fixed event is, the better for the organisation to synchronise, and plan around it.
The benefit of the annual plan can also be illustrated using the example of the board meeting. If the event is set at the same time each year, it becomes routine. Everyone knows when it will occur, and will start preparing their input for the meeting. If (as is common) busy managers first realise there is an impending board meeting when they receive the invitation to attend (and present) one week prior to the meeting (which can be dictated by national labour law, or company bylaws) it is disruptive. Managers are not always called to present at board meetings, but they will most usually be expected to provide data and materials. If, however, managers know that the board meeting will always be held in the last week of January, they can either block time or avoid accepting new work the week before when they will need to prepare for the board meeting.
It seems (and is) a very simple thing to do, and obvious once you know. I have presented this idea at multiple companies and customers, and the outcome has only been positive.

## Annual Plan
No. |  | Events | Per | Timing | Responsible | Receiver(s) | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4
|  |  | Per | Timing | Responsible | Receiver(s) | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December
[7 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53
CET | time axis 2025-12-29 to 2026-12-28
101 | •
102 | •
103 | •
104 | •
105 | •
106 | •
100 | Shareholders / Board of Directors
201 | •
202 | •
203 | •
204 | •
200 | Marketing & Sales
301 | •
302 | •
303 | •
304 | •
300 | Human Resources
401 | •
402 | •
403 | •
404 | •
400 | Finance
501 | •
502 | •
503 | •
504 | •
500 | Legal / Compliance
601 | •
602 | •
603 | •
604 | •
600 | Operations / Delivery

## Menu (hidden)
Month | Name
1 | January
2 | February
3 | March
4 | April
5 | May
6 | June
7 | July
8 | August
9 | September
10 | October
11 | November
12 | December